## Sheet1
Task ID | Task Name | Weightage | Start | Finish | Planned Qty | Actual Qty | % of Completion | Planned Progress % | Progress Variance | Actual Cost | Progress Remarks
SIWMF Application Basline |  |  |  |  | 175 | 0 | 66.02% | 96.73% | -30.72%
SIWMF Submission
0 | SIWMF Baseline
A1000 | Contract Award | 0.01532% | 2021-03-09 | 2021-03-09 | 1 | 100% | 0.01532% | 0.01532% | 0% | 100%
A1020.14 | Detailed Design for weighbridge MD2/AD2 Review and Acceptance by SO | 0% | 2022-01-21 | 2022-01-21 | 1 | 100% | 0% | 0% | 0% | 100%
A1070.F.05 | Successful Completion of Factory acceptance Test(FAT) | 0% | 2023-10-24 | 2023-10-24 | 1 | 0% | 0% | 0% | 0% | 0%
A1080.D.06 | Time for Delivery of Weighbridge System | 0% | 2024-01-02 | 2024-01-02 | 1 | 0% | 0% | 0% | 0% | 0%
A1090.I.22 | Completion of Weighbridge Mechanical , EIAC and Zonal Detection System | 0% | 2024-05-15 | 2024-05-15 | 1 | 0% | 0% | 0% | 0% | 0%
A1110.S.04 | Successful SAT of Weighbridge system | 0% | 2024-07-31 | 2024-07-31 | 1 | 0% | 0% | 0 | 0% | 0%
A1130.15 | Successful Completion of Trial Operation | 0% | 2025-07-09 | 2025-07-09 | 1 | 0% | 0% | 0% | 0% | 0%
A1160 | Completion of the whole of the Sub-Contract Works | 0% | 2025-10-07 | 2025-10-07 | 1 | 0% | 0% | 0% | 0% | 0%
0 | Process Engineering (Detailed Design Milestone)
A1010 | MD1 AD1 Preparation, Submission, Review & Acceptance | 0.1836% | 2021-03-19 | 2021-04-03 | 1 | 100% | 0.1836% | 0.1836% | 0% | 100%
A1020 | MD2 ED1 AD2 Preparation, Submission, Review & Acceptance
A1020.1 | MD2 Weighbridge System Package (Rev 0a) Preparation by ALC | 0.979% | 2021-04-07 | 2021-06-16 | 1 | 100% | 0.979% | 0.979% | 0% | 100%
A1020.2 | MD2 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.01721% | 2021-06-17 | 2021-06-17 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1020.3 | MD2 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.1205% | 2021-06-18 | 2021-06-25 | 1 | 100% | 0.1205% | 0.1205% | 0% | 100%
A1020.4 | MD2 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.3633% | 2021-06-26 | 2021-07-21 | 1 | 100% | 0.3633% | 0.3633% | 0% | 100%
A1020.5 | MD2 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.05352% | 2021-07-22 | 2021-07-26 | 1 | 100% | 0.05352% | 0.05352% | 0% | 100%
A1020.6 | MD2 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.0191% | 2021-07-28 | 2021-07-29 | 1 | 100% | 0.0191% | 0.0191% | 0% | 100%
A1020.7 | MD2 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0.1377% | 2021-07-30 | 2021-08-08 | 1 | 100% | 0.1377% | 0.1377% | 0% | 100%
A1020.1 | ED1 AD2 Weighbridge System Package (Rev 0a) Preparation by ALC | 1.099% | 2021-04-07 | 2021-06-24 | 1 | 100% | 1.099% | 1.099% | 0% | 100%
A1020.2 | ED1 AD2 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.01721% | 2021-06-25 | 2021-06-25 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1020.3 | ED1 AD2 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.1051% | 2021-06-25 | 2021-07-02 | 1 | 100% | 0.1051% | 0.1051% | 0% | 100%
A1020.4 | ED1 AD2 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.2046% | 2021-07-03 | 2021-07-16 | 1 | 100% | 0.2046% | 0.2046% | 0% | 100%
A1020.5 | ED1 AD2 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.1377% | 2021-07-17 | 2021-07-26 | 1 | 100% | 0.1377% | 0.1377% | 0% | 100%
A1020.6 | ED1 AD2 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.06883% | 2021-07-27 | 2021-07-30 | 1 | 100% | 0.06883% | 0.06883% | 0% | 100%
A1020.7 | ED1 AD2 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0.3442% | 2021-08-04 | 2021-08-27 | 1 | 100% | 0.3442% | 0.3442% | 0% | 100%
A1020.8 | MD2 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO Comments and Re-submission to KSPL | 0.499% | 2021-08-28 | 2021-09-30 | 1 | 100% | 0.499% | 0.499% | 0% | 100%
A1020.9 | MD2 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.2065% | 2021-09-22 | 2021-10-05 | 1 | 100% | 0.2065% | 0.2065% | 0% | 100%
A1020.10 | MD2 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.1549% | 2021-10-06 | 2021-10-15 | 1 | 100% | 0.1549% | 0.1549% | 0% | 100%
A1020.11 | MD2 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.06883% | 2021-10-16 | 2021-10-20 | 1 | 100% | 0.06883% | 0.06883% | 0% | 100%
A1020.12 | MD2 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.06883% | 2021-10-21 | 2021-10-25 | 1 | 100% | 0.06883% | 0.06883% | 0% | 100%
A1020.13 | MD2 Weighbridge System Package (Rev 1) Review by SO/ NEA(Accepted with comments , Re-submission Required) | 1.205% | 2021-10-29 | 2022-01-21 | 1 | 100% | 1.205% | 1.205% | 0% | 100%
A1020.14 | MD2 Weighbridge System Package (Rev XX) Review by SO/ NEA(Accepted with comments , No Re-submission Required) | 0% | 2022-01-24 | 2023-01-30 | 1 | 100% | 0% | 0% | 0% | 100%
A1020.8 | ED1 AD2 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO Comments and Re-submission to KSPL | 0.499% | 2021-08-28 | 2021-09-30 | 1 | 100% | 0.499% | 0.499% | 0% | 100%
A1020.9 | ED1 AD2 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.1912% | 2021-09-30 | 2021-10-14 | 1 | 100% | 0.1912% | 0.1912% | 0% | 100%
A1020.10 | ED1 AD2 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.1721% | 2021-10-14 | 2021-10-26 | 1 | 100% | 0.1721% | 0.1721% | 0% | 100%
A1020.11 | ED1 AD2 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.0191% | 2021-10-26 | 2021-10-28 | 1 | 100% | 0.0191% | 0.0191% | 0% | 100%
A1020.12 | ED1 AD2 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.01721% | 2021-10-28 | 2021-10-29 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1020.13 | ED1 AD2 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0.1377% | 2021-10-29 | 2021-11-08 | 1 | 100% | 0.1377% | 0.1377% | 0% | 100%
A1020.14 | AD2 Weighbridge System Package (Rev 1) Review by SO/ NEA(Accepted with comments , Re-submission Required) | 1.222% | 2021-10-29 | 2022-01-22 | 1 | 100% | 1.222% | 1.222% | 0% | 100%
A1020.15 | AD2 Weighbridge System Package (Rev XX) Review by SO/ NEA(Accepted with comments , Re-submission Required) | 0% | 2022-01-24 | 2023-07-08 | 1 | 100% | 0% | 0% | 0% | 100%
A1030 | MD3 ED2 ED3 AD3 Preparation, Submission, Review & Acceptance
A1030.1 | MD3 Preparation, Submission, Review & Acceptance
A1030.1 | MD3 Weighbridge System Package (Rev 0a) Preparation by ALC | 0.1721% | 2022-06-25 | 2022-07-06 | 1 | 100% | 0.1721% | 0.1721% | 0% | 100%
A1030.2 | MD3 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.05163% | 2022-07-07 | 2022-07-09 | 1 | 100% | 0.05163% | 0.05163% | 0% | 100%
A1030.3 | MD3 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.1893% | 2022-07-12 | 2022-07-23 | 1 | 100% | 0.1893% | 0.1893% | 0% | 100%
A1030.4 | MD3 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.05163% | 2022-07-25 | 2022-07-27 | 1 | 100% | 0.05163% | 0.05163% | 0% | 100%
A1030.5 | MD3 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.1377% | 2022-07-28 | 2022-08-05 | 1 | 100% | 0.1377% | 0.1377% | 0% | 100%
A1030.6 | MD3 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.08604% | 2022-08-06 | 2022-08-12 | 1 | 100% | 0.08604% | 0.08604% | 0% | 100%
A1030.7 | MD3 Weighbridge System Package (Rev 0) Review by SO/ NEA | 1.136% | 2022-08-13 | 2022-09-01 | 1 | 100% | 1.136% | 1.136% | 0% | 100%
A1030.8 | MD3 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO comments and Re-submission to KSPL | 0.2986% | 2022-09-02 | 2022-09-09 | 1 | 100% | 0.2986% | 0.2986% | 0% | 100%
A1030.9 | MD3 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.01721% | 2022-09-10 | 2022-09-16 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1030.10 | MD3 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.01721% | 2022-09-17 | 2022-09-21 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1030.11 | MD3 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.01721% | 2022-09-22 | 2022-09-29 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1030.12 | MD3 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.01721% | 2022-09-30 | 2022-10-04 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1030.13 | MD3 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0.3528% | 2022-10-05 | 2022-10-25 | 1 | 100% | 0.3528% | 0.3528% | 0% | 100%
A1030.14 | MD3 Weighbridge System Package (Review 2 and above monitored accepted with comments, No Re-submission Required) | 0.4646% | 2022-10-26 | 2022-11-25 | 1 | 100% | 0.4646% | 0.4646% | 0% | 100%
A1030.2 | ED2 Preparation, Submission, Review & Acceptance | 18.39% | 2021-06-18 | 2023-07-14 | 1 | 100% | 18.39% | 18.39% | 0% | 100%
A1030.2.1 | ED2 Weighbridge System Package (Rev 0a) Preparation by ALC | 1.153% | 2021-06-18 | 2021-09-04 | 1 | 100% | 1.153% | 1.153% | 0% | 100%
A1030.2.2 | ED2 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.03442% | 2021-09-06 | 2021-09-07 | 1 | 100% | 0.03442% | 0.03442% | 0% | 100%
A1030.2.3 | ED2 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.2065% | 2021-09-08 | 2021-09-21 | 1 | 100% | 0.2065% | 0.2065% | 0% | 100%
A1030.2.4 | ED2 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.1377% | 2021-09-22 | 2021-09-30 | 1 | 100% | 0.1377% | 0.1377% | 0% | 100%
A1030.2.5 | ED2 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.1033% | 2021-10-01 | 2021-10-07 | 1 | 100% | 0.1033% | 0.1033% | 0% | 100%
A1030.2.6 | ED2 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.1377% | 2021-10-07 | 2021-10-15 | 1 | 100% | 0.1377% | 0.1377% | 0% | 100%
A1030.2.7 | ED2 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0.1893% | 2022-05-06 | 2022-05-18 | 1 | 100% | 0.1893% | 0.1893% | 0% | 100%
A1030.2.8 | ED2 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO comments and Re-submission to KSPL | 0.5163% | 2022-05-19 | 2022-06-22 | 1 | 100% | 0.5163% | 0.5163% | 0% | 100%
A1030.2.9 | ED2 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.1033% | 2022-06-23 | 2022-06-29 | 1 | 100% | 0.1033% | 0.1033% | 0% | 100%
A1030.2.10 | ED2 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.4493% | 2022-06-30 | 2022-08-01 | 1 | 100% | 0.4493% | 0.4493% | 0% | 100%
A1030.2.11 | ED2 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.1224% | 2022-08-02 | 2022-08-11 | 1 | 100% | 0.1224% | 0.1224% | 0% | 100%
A1030.2.12 | ED2 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.1377% | 2022-08-12 | 2022-08-20 | 1 | 100% | 0.1377% | 0.1377% | 0% | 100%
A1030.2.13 | ED2 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0.1721% | 2022-08-23 | 2022-09-02 | 1 | 100% | 0.1721% | 0.1721% | 0% | 100%
A1030.2.14 | ED2 Weighbridge System Package (Review 2 and above monitored accepted with comments, No Re-submission Required) | 0.4665% | 2022-09-05 | 2023-07-14 | 1 | 100% | 0.4665% | 0.4665% | 0% | 100%
A1030.3 | ED3 Preparation, Submission, Review & Acceptance
A1030.3.1 | ED3 Weighbridge System Package (Rev 0a) Preparation by ALC | 0.1893% | 2022-09-03 | 2022-10-05 | 1 | 100% | 0.1893% | 0.1893% | 0% | 100%
A1030.3.2 | ED3 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.03442% | 2022-10-04 | 2022-10-05 | 1 | 100% | 0.03442% | 0.03442% | 0% | 100%
A1030.3.3 | ED3 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.03442% | 2022-10-07 | 2022-10-19 | 1 | 100% | 0.03442% | 0.03442% | 0% | 100%
A1030.3.4 | ED3 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.03442% | 2022-10-20 | 2022-10-26 | 1 | 100% | 0.03442% | 0.03442% | 0% | 100%
A1030.3.5 | ED3 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.03442% | 2022-10-28 | 2022-11-04 | 1 | 100% | 0.03442% | 0.03442% | 0% | 100%
A1030.3.6 | ED3 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.03442% | 2022-11-05 | 2022-11-09 | 1 | 100% | 0.03442% | 0.03442% | 0% | 100%
A1030.3.7 | ED3 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0% | 2022-11-09 | 2022-11-07 | 1 | 100% | 0% | 0% | 0% | 100%
A1030.3.8 | ED3 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO comments and Re-submission to KSPL | 0.09637% | 2022-11-28 | 2022-12-05 | 1 | 100% | 0.09637% | 0.09637% | 0% | 100%
A1030.3.9 | ED3 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.01721% | 2022-12-06 | 2022-12-12 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1030.3.10 | ED3 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0% | 2022-12-13 | 2022-12-16 | 1 | 100% | 0% | 0% | 0% | 100%
A1030.3.11 | ED3 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.01721% | 2022-12-17 | 2022-12-23 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1030.3.12 | ED3 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.1033% | 2022-12-24 | 2022-12-29 | 1 | 100% | 0.1033% | 0.1033% | 0% | 100%
A1030.3.13 | ED3 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0.3098% | 2022-12-31 | 2023-01-19 | 1 | 100% | 0.3098% | 0.3098% | 0% | 100%
A1030.3.13 | ED3 Weighbridge System Package (Review 2 and above monitored accepted with comments, No Re-submission Required) | 0.4646% | 2023-06-21 | 2023-07-22 | 1 | 100% | 0.4646% | 0.4646% | 0% | 100%
A1030.4 | AD3 Preparation, Submission, Review & Acceptance
A1030.4.1 | AD3 Weighbridge System Package (Rev 0a) Preparation by ALC | 2.134% | 2022-02-10 | 2022-07-07 | 1 | 100% | 2.134% | 2.134% | 0% | 100%
A1030.4.2 | AD3 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.3098% | 2022-07-08 | 2022-07-20 | 1 | 100% | 0.3098% | 0.3098% | 0% | 100%
A1030.4.3 | AD3 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.03442% | 2022-07-21 | 2022-07-22 | 1 | 100% | 0.03442% | 0.03442% | 0% | 100%
A1030.4.4 | AD3 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.3098% | 2022-07-22 | 2022-07-28 | 1 | 100% | 0.3098% | 0.3098% | 0% | 100%
A1030.4.5 | AD3 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.1377% | 2022-07-29 | 2022-09-05 | 1 | 100% | 0.1377% | 0.1377% | 0% | 100%
A1030.4.6 | AD3 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.03442% | 2022-09-07 | 2022-09-14 | 1 | 100% | 0.03442% | 0.03442% | 0% | 100%
A1030.4.7 | AD3 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0% | 2022-09-14 | 2022-09-27 | 1 | 100% | 0% | 0% | 0% | 100%
A1030.4.8 | AD3 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO comments and Re-submission to KSPL | 0.6367% | 2022-09-29 | 2022-10-04 | 1 | 100% | 0.6367% | 0.6367% | 0% | 100%
A1030.4.9 | AD3 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.3442% | 2022-10-05 | 2022-11-30 | 1 | 100% | 0.3442% | 0.3442% | 0% | 100%
A1030.4.10 | AD3 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.4302% | 2022-12-01 | 2022-12-30 | 1 | 100% | 0.4302% | 0.4302% | 0% | 100%
A1030.4.11 | AD3 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.1205% | 2022-12-31 | 2023-01-09 | 1 | 100% | 0.1205% | 0.1205% | 0% | 100%
A1030.4.12 | AD3 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.06883% | 2023-01-10 | 2023-01-13 | 1 | 100% | 0.06883% | 0.06883% | 0% | 100%
A1030.4.13 | AD3 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0% | 2023-01-14 | 2023-02-04 | 1 | 100% | 0% | 0% | 0% | 100%
A1030.4.14 | AD3 Weighbridge System Package (Review 2 and above monitored accepted with comments, No Re-submission Required) | 0.2753% | 2023-06-21 | 2023-07-10 | 1 | 100% | 0.2753% | 0.2753% | 0% | 100%
A1085 | Traffic Modelling
A1085.T.01 | Award Traffic Modelling Consultant | 0.01721% | 2022-02-07 | 2022-02-07 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1085.T.02 | Kick-off Meeting | 0.02685% | 2022-02-22 | 2022-02-23 | 1 | 100% | 0.02685% | 0.02685% | 0% | 100%
A1085.T.03 | First round of model findings in slides [Rev 0a] | 0.4818% | 2022-02-24 | 2022-03-28 | 1 | 100% | 0.4818% | 0.4818% | 0% | 100%
A1085.T.04 | Comments on Rev 0a findings (allowing time for possible discussion and presentation) | 0.1205% | 2022-03-29 | 2022-04-05 | 1 | 100% | 0.1205% | 0.1205% | 0% | 100%
A1085.T.05 | Second round of model findings in slides [Rev 0b] | 0.03442% | 2022-04-06 | 2022-04-07 | 1 | 100% | 0.03442% | 0.03442% | 0% | 100%
A1085.T.06 | Submit to SO/ NEA [Rev 0] | 1.067% | 2022-04-08 | 2022-06-22 | 1 | 100% | 1.067% | 1.067% | 0% | 100%
A1085.T.07 | Third round of model findings in slides [Rev 1a] | 2.291% | 2022-06-23 | 2022-11-29 | 1 | 100% | 2.291% | 2.291% | 0% | 100%
A1085.T.08 | Comments on Rev 1a findings (allowing time for possible discussion and presentation) | 0.05163% | 2022-09-30 | 2022-10-03 | 1 | 100% | 0.05163% | 0.05163% | 0% | 100%
A1085.T.09 | Fourth round of model findings in slides [Rev 1b] | 0.1224% | 2022-10-04 | 2022-10-12 | 1 | 100% | 0.1224% | 0.1224% | 0% | 100%
A1085.T.10 | Submit to SO/ NEA [Rev 1] | 0.587% | 2022-10-13 | 2022-12-05 | 1 | 100% | 0.587% | 0.587% | 0% | 100%
A1085.T.11 | Fifth round of model findings in slides [Rev 2a] | 0.01721% | 2022-12-06 | 2022-12-13 | 1 | 100% | 0.01721% | 0.01721% | 0% | 100%
A1085.T.12 | Comments on Rev 2a findings (allowing time for possible discussion and presentation) | 0% | 2022-12-14 | 2022-12-23 | 1 | 100% | 0% | 0% | 0% | 100%
A1085.T.13 | Sixth round of model findings in slides [Rev 2b] | 0% | 2022-12-24 | 2023-01-03 | 1 | 100% | 0% | 0% | 0% | 100%
A1085.T.14 | Submit to SO/ NEA [Rev 2] | 0% | 2023-01-04 | 2023-01-14 | 1 | 100% | 0% | 0% | 0% | 100%
A1085.T.15 | Final Model findings report | 0.1893% | 2023-01-16 | 2023-01-21 | 1 | 100% | 0.1893% | 0.1893% | 0% | 100%
A1085.T.16 | Final presentation / confirmation on findings | 2.564% | 2023-01-25 | 2023-02-03 | 1 | 100% | 2.564% | 2.564% | 0% | 100%
A1085.T.17 | Comments on final report | 0.8432% | 2023-02-06 | 2023-02-08 | 1 | 100% | 0.8432% | 0.8432% | 0% | 100%
A1085.T.18 | Submit & Confirmation of final report by SO/NEA | 0.06883% | 2023-02-09 | 2023-02-13 | 1 | 100% | 0.06883% | 0.06883% | 0% | 100%
A1050 | Procurement
A1050.P.01 | Weighbridges | 1.859% | 2022-08-26 | 2023-03-15 | 1 | 100% | 1.859% | 1.859% | 0% | 100%
A1050.P.02 | Furniture | 0.8948% | 2023-02-14 | 2023-04-15 | 1 | 95% | 0.8501% | 0.8948% | -0.04474% | 95%
A1050.P.03 | UPS & 19" Racks | 0% | 2022-10-18 | 2023-03-16 | 1 | 100% | 0% | 0% | 0% | 100%
A1050.P.04 | Public Announcement System | 0.4646% | 2021-07-05 | 2023-03-16 | 1 | 85% | 0.3949% | 0.4646% | -0.06969% | 85%
A1050.P.05 | Electrical & Structured Cabling Services(By Others) | 0.4646% | 2023-02-14 | 2023-03-16 | 1 | 0% | 0% | 0.4646% | -0.4646% | 0%
A1050.P.06 | Data Processing Equipment | 0.4646% | 2022-05-25 | 2023-03-16 | 1 | 100% | 0.4646% | 0.4646% | 0% | 100%
A1050.P.07 | Data Communication Equipment | 0.4646% | 2022-05-25 | 2023-03-16 | 1 | 95% | 0.4414% | 0.4646% | -0.02323% | 95%
A1050.P.08 | Station Integrated with Interfacing Controller for Receipt, Intercom, RFID, Biometrics, Traffic Lights, Vehicle Barrier | 0.4646% | 2022-05-25 | 2023-03-16 | 1 | 95% | 0.4414% | 0.4646% | -0.02323% | 95%
A1050.P.09 | Video Recording System, LPR Hardware and Accessories | 0.6195% | 2022-05-25 | 2023-03-27 | 1 | 95% | 0.5885% | 0.6195% | -0.03098% | 95%
A1050.P.10 | Zonal Detection System | 0.8776% | 2022-05-25 | 2023-04-14 | 1 | 85% | 0.746% | 0.8776% | -0.1316% | 85%
A1050.P.11 | Radioactive Devices | 0.8948% | 2022-08-29 | 2023-04-15 | 1 | 100% | 0.8948% | 0.8948% | 0% | 100%
A1050.P.12 | Heat Detection Devices | 1.549% | 2022-08-09 | 2023-03-10 | 1 | 100% | 1.549% | 1.549% | 0% | 100%
A1050.P.13 | Ash Truck Positioning and Empty/Full Detection Devices | 0.8948% | 2022-05-25 | 2023-04-15 | 1 | 80% | 0.7159% | 0.8948% | -0.179% | 80%
A1050.P.14 | Purchase and Delivery of Casted Items(Others) -Batch 1 | 1.205% | 2023-06-09 | 2023-06-10 | 1 | 100% | 1.205% | 1.205% | 0% | 100%
A1050.P.15 | Purchase and Delivery of Casted Items(Others) - Batch 2 | 1.325% | 2023-06-10 | 2023-06-10 | 1 | 100% | 1.325% | 1.325% | 0% | 100%
0 | Manufacture / Fabrication / Delivery
A1060 | Manufacture Commence Data (Commence Date should be notified by KSPL)
A1060.M.01 | Weighbridges | 0.9293% | 2023-03-16 | 2023-05-20 | 1 | 100% | 0.9293% | 0.9293% | 0% | 100%
A1060.M.02 | Furniture | 0.4646% | 2023-04-17 | 2023-05-19 | 1 | 0% | 0% | 0.4646% | -0.4646% | 0%
A1060.M.03 | UPS & 19" Racks | 0.9293% | 2023-03-17 | 2023-05-22 | 1 | 80% | 0.7434% | 0.9293% | -0.1859% | 80%
A1060.M.04 | Public Announcement System | 0.6023% | 2023-03-17 | 2023-04-28 | 1 | 50% | 0.3011% | 0.6023% | -0.3011% | 50%
A1060.M.05 | Electrical & Structured Cabling Services | 1.377% | 2023-03-17 | 2023-06-21 | 1 | 0% | 0% | 1.377% | -1.377% | 0%
A1060.M.06 | Data Processing Equipment | 0.9293% | 2023-03-17 | 2023-05-22 | 1 | 40% | 0.3717% | 0.9293% | -0.5576% | 40%
A1060.M.07 | Data Communication Equipment | 0.9293% | 2023-05-02 | 2023-07-04 | 1 | 40% | 0.3717% | 0.9293% | -0.5576% | 40%
A1060.M.08 | Station Integrated with Interfacing Controller for Receipt, Intercom, RFID, Biometrics, Traffic Lights, Vehicle Barrier | 1.377% | 2023-03-17 | 2023-06-21 | 1 | 60% | 0.826% | 1.377% | -0.5507% | 60%
A1060.M.09 | Video Recording System, LPR Hardware and Accessories | 1.084% | 2023-03-28 | 2023-06-12 | 1 | 70% | 0.7589% | 1.084% | -0.3252% | 70%
A1060.M.10 | Zonal Detection System | 1.377% | 2023-05-23 | 2023-08-25 | 1 | 30% | 0.413% | 1.377% | -0.9637% | 30%
A1060.M.11 | Radioactive Devices | 0.6195% | 2023-04-17 | 2023-05-30 | 1 | 90% | 0.5576% | 0.6195% | -0.06195% | 90%
A1060.M.12 | Heat Detection Devices | 0.7744% | 2023-03-11 | 2023-05-05 | 1 | 80% | 0.6195% | 0.7744% | -0.1549% | 80%
A1060.M.13 | Ash Truck Positioning and Empty/Full Detection Devices | 0.9293% | 2023-04-17 | 2023-06-20 | 1 | 35% | 0.3252% | 0.9293% | -0.604% | 35%
A1070 | Completion of FAT for Weighbridge System
A1070.F.01 | FAT for Weighbridge | 0.8776% | 2023-07-24 | 2023-09-21 | 1 | 0% | 0% | 0.8776% | -0.8776% | 0%
A1070.F.02 | FAT for Zonal Detection | 0.7744% | 2023-08-26 | 2023-10-17 | 1 | 0% | 0% | 0.7744% | -0.7744% | 0%
A1070.F.03 | FAT for Ash Truck Positioning and Empty/Full Detection Devices | 0.7744% | 2023-07-05 | 2023-08-26 | 1 | 0% | 0% | 0.7744% | -0.7744% | 0%
A1070.F.04 | Preparation of Holding Area for weighbridge platforms | 0.06883% | 2023-10-20 | 2023-10-24 | 1 | 0% | 0% | 0.06883% | -0.06883% | 0%
A1080 | Delivery to Site
A1080.D.00 | Architectural and Building Service Works | 0.01532% | 2023-09-22 | 2023-09-22 | 1 | 0% | 0% | 0.01532% | -0.01532% | 0%
A1080.D.01 | Weighbridge System delivery | 0.9809% | 2023-10-25 | 2024-01-02 | 1 | 0% | 0% | 0.9809% | -0.9809% | 0%
A1080.D.02 | Other Weighbridge Equipments | 0.9809% | 2023-10-25 | 2024-01-02 | 1 | 0% | 0% | 0.9809% | -0.9809% | 0%
A1080.D.03 | Weighbridge Platform | 0.9809% | 2023-10-25 | 2024-01-02 | 1 | 0% | 0% | 0.9809% | -0.9809% | 0%
A1080.D.04 | Zonal Detection System delivery | 0.6195% | 2023-10-25 | 2023-12-06 | 1 | 0% | 0% | 0.6195% | -0.6195% | 0%
A1080.D.05 | Ash Truck Positioning and Empty/Full Detection Devices delivery | 0.6195% | 2023-10-25 | 2023-12-06 | 1 | 0% | 0% | 0.6195% | -0.6195% | 0%
A1090 | Installation
A1090.I.01 | Weighbridge Foundation & Control Room ready for Installation | 0.05163% | 2024-01-03 | 2024-01-05 | 1 | 0% | 0% | 0.05163% | -0.05163% | 0%
A1090.I.02 | Electrical and instrumentation works | 0.01721% | 2024-01-06 | 2024-01-06 | 1 | 0% | 0% | 0.01721% | -0.01721% | 0%
A1090.I.03 | Public Announcement System | 0.6195% | 2024-01-08 | 2024-02-20 | 1 | 0% | 0% | 0.6195% | -0.6195% | 0%
A1090.I.04 | Weighbridges | 1.652% | 2024-01-19 | 2024-05-15 | 1 | 0% | 0% | 1.652% | -1.652% | 0%
A1090.I.05 | Furniture | 0.3098% | 2024-01-08 | 2024-01-27 | 1 | 0% | 0% | 0.3098% | -0.3098% | 0%
A1090.I.06 | Rack | 0.3098% | 2024-01-08 | 2024-01-27 | 1 | 0% | 0% | 0.3098% | -0.3098% | 0%
A1090.I.07 | UPS | 0.3098% | 2024-01-08 | 2024-01-27 | 1 | 0% | 0% | 0.3098% | -0.3098% | 0%
A1090.I.08 | Data Processing System (DPS) | 0.4646% | 2024-01-08 | 2024-02-07 | 1 | 0% | 0% | 0.4646% | -0.4646% | 0%
A1090.I.09 | Data Communication System | 0.4646% | 2024-01-08 | 2024-02-07 | 1 | 0% | 0% | 0.4646% | -0.4646% | 0%
A1090.I.10 | Interfacing Controller (IFC) | 0.3098% | 2024-01-08 | 2024-01-27 | 1 | 0% | 0% | 0.3098% | -0.3098% | 0%
A1090.I.11 | Weighbridge Intercom Kiosk | 0.8604% | 2024-01-08 | 2024-03-07 | 1 | 0% | 0% | 0.8604% | -0.8604% | 0%
A1090.I.12 | EPS Antenna | 0.4474% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4474% | -0.4474% | 0%
A1090.I.13 | Traffic Lights | 0.4474% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4474% | -0.4474% | 0%
A1090.I.14 | Barriers | 0.4474% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4474% | -0.4474% | 0%
A1090.I.15 | License Plate Recognition System (LPR) | 0.4474% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4474% | -0.4474% | 0%
A1090.I.16 | Video Recording System (VRS) | 0.4474% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4474% | -0.4474% | 0%
A1090.I.17 | Radioactive Devices | 0.413% | 2024-01-08 | 2024-02-03 | 1 | 0% | 0% | 0.413% | -0.413% | 0%
A1090.I.18 | Load Heat Detection Devices | 0.413% | 2024-01-08 | 2024-02-03 | 1 | 0% | 0% | 0.413% | -0.413% | 0%
A1090.I.19 | Single weighbridge physical mock-up | 0.6367% | 2024-01-08 | 2024-02-21 | 1 | 0% | 0% | 0.6367% | -0.6367% | 0%
A1090.I.20 | Zonal Detection System | 0.6539% | 2024-01-08 | 2024-02-22 | 1 | 0% | 0% | 0.6539% | -0.6539% | 0%
A1090.I.21 | Ash Truck Positioning and Empty/Full Detection Devices | 0.8604% | 2024-01-08 | 2024-03-07 | 1 | 0% | 0% | 0.8604% | -0.8604% | 0%
0 | Testing & Commissioning
A1100 | ERP/ DCS Interface Readiness | 0.01721% | 2024-05-30 | 2024-05-30 | 1 | 0% | 0% | 0.01721% | -0.01721% | 0%
A1110 | Site Acceptance Test
A1110.S.01 | Client Inspection of Weighbridge Sub-system | 0.4302% | 2024-05-31 | 2024-06-29 | 1 | 0% | 0% | 0.4302% | -0.4302% | 0%
A1110.S.02 | Client Inspection of Zonal Detection Sub-system | 0.4646% | 2024-07-01 | 2024-07-31 | 1 | 0% | 0% | 0.4646% | -0.4646% | 0%
A1110.S.03 | Punchlist Clearance | 0.3442% | 2024-08-01 | 2024-08-23 | 1 | 0% | 0% | 0.3442% | -0.3442% | 0%
A1110.S.04 | User Training | 0.3098% | 2024-08-24 | 2024-09-13 | 1 | 0% | 0% | 0.3098% | -0.3098% | 0%
A1120 | System Commissioning Test
A1120.S.01 | Weighbridge (Line 1&2) System Conduct System Commissioning Test - Hardware | 1.377% | 2024-09-14 | 2024-12-16 | 1 | 0% | 0% | 1.377% | -1.377% | 0%
A1120.S.02 | Weighbridge (Line 1&2) System Conduct System Commissioning Test - Software | 1.377% | 2024-09-14 | 2024-12-16 | 1 | 0% | 0% | 1.377% | -1.377% | 0%
A1120.S.03 | Weighbridge Zonal System Conduct System Commissioning Test | 1.377% | 2024-09-14 | 2024-12-16 | 1 | 0% | 0% | 1.377% | -1.377% | 0%
A1120.S.04 | Weighbridge (Line 3&4) System Commissioning Test | 1.377% | 2024-12-17 | 2025-03-19 | 1 | 0% | 0% | 0.6734% | -0.6734% | 0%
A1130 | Successful Completion of Trial Operation Test | 1.635% | 2025-03-21 | 2025-07-09 | 1 | 0% | 0% | 0% | 0% | 0%
A1150 | Completion of the whole Sub-Contract Works | 0.9293% | 2025-07-10 | 2025-10-07 | 1 | 0% | 0% | 0% | 0% | 0%
Formulas:
Start = [1]ALC!D8
Finish = [1]ALC!E8

## Sheet2
Task ID | Task Name | Weightage | Start | Finish | Planned Qty | Actual Qty | % of Completion | Planned Progress % | Progress Variance | Actual Cost | Progress Remarks
SIWMF Application Basline |  |  |  |  | 175 | 0 | 64.1% | 97.26% | -33.16%
SIWMF Submission
0 | SIWMF Baseline
A1000 | Contract Award | 0.01473% | 2021-03-09 | 2021-03-09 | 1 | 100% | 0.01473% | 0.01473% | 0% | 100%
A1020.14 | Detailed Design for weighbridge MD2/AD2 Review and Acceptance by SO | 0% | 2022-01-21 | 2022-01-21 | 1 | 100% | 0% | 0% | 0% | 100%
A1070.F.05 | Successful Completion of Factory acceptance Test(FAT) | 0% | 2023-10-24 | 2023-10-24 | 1 | 0% | 0% | 0% | 0% | 0%
A1080.D.06 | Time for Delivery of Weighbridge System | 0% | 2024-01-02 | 2024-01-02 | 1 | 0% | 0% | 0% | 0% | 0%
A1090.I.22 | Completion of Weighbridge Mechanical , EIAC and Zonal Detection System | 0% | 2024-05-15 | 2024-05-15 | 1 | 0% | 0% | 0% | 0% | 0%
A1110.S.04 | Successful SAT of Weighbridge system | 0% | 2024-07-31 | 2024-07-31 | 1 | 0% | 0% | 0 | 0% | 0%
A1130.15 | Successful Completion of Trial Operation | 0% | 2025-07-09 | 2025-07-09 | 1 | 0% | 0% | 0% | 0% | 0%
A1160 | Completion of the whole of the Sub-Contract Works | 0% | 2025-10-07 | 2025-10-07 | 1 | 0% | 0% | 0% | 0% | 0%
0 | Process Engineering (Detailed Design Milestone)
A1010 | MD1 AD1 Preparation, Submission, Review & Acceptance | 0.1766% | 2021-03-19 | 2021-04-03 | 1 | 100% | 0.1766% | 0.1766% | 0% | 100%
A1020 | MD2 ED1 AD2 Preparation, Submission, Review & Acceptance
A1020.1 | MD2 Weighbridge System Package (Rev 0a) Preparation by ALC | 0.9416% | 2021-04-07 | 2021-06-16 | 1 | 100% | 0.9416% | 0.9416% | 0% | 100%
A1020.2 | MD2 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.01655% | 2021-06-17 | 2021-06-17 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1020.3 | MD2 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.1159% | 2021-06-18 | 2021-06-25 | 1 | 100% | 0.1159% | 0.1159% | 0% | 100%
A1020.4 | MD2 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.3494% | 2021-06-26 | 2021-07-21 | 1 | 100% | 0.3494% | 0.3494% | 0% | 100%
A1020.5 | MD2 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.05147% | 2021-07-22 | 2021-07-26 | 1 | 100% | 0.05147% | 0.05147% | 0% | 100%
A1020.6 | MD2 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.01837% | 2021-07-28 | 2021-07-29 | 1 | 100% | 0.01837% | 0.01837% | 0% | 100%
A1020.7 | MD2 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0.1324% | 2021-07-30 | 2021-08-08 | 1 | 100% | 0.1324% | 0.1324% | 0% | 100%
A1020.1 | ED1 AD2 Weighbridge System Package (Rev 0a) Preparation by ALC | 1.057% | 2021-04-07 | 2021-06-24 | 1 | 100% | 1.057% | 1.057% | 0% | 100%
A1020.2 | ED1 AD2 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.01655% | 2021-06-25 | 2021-06-25 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1020.3 | ED1 AD2 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.1011% | 2021-06-25 | 2021-07-02 | 1 | 100% | 0.1011% | 0.1011% | 0% | 100%
A1020.4 | ED1 AD2 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.1968% | 2021-07-03 | 2021-07-16 | 1 | 100% | 0.1968% | 0.1968% | 0% | 100%
A1020.5 | ED1 AD2 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.1324% | 2021-07-17 | 2021-07-26 | 1 | 100% | 0.1324% | 0.1324% | 0% | 100%
A1020.6 | ED1 AD2 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.0662% | 2021-07-27 | 2021-07-30 | 1 | 100% | 0.0662% | 0.0662% | 0% | 100%
A1020.7 | ED1 AD2 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0.331% | 2021-08-04 | 2021-08-27 | 1 | 100% | 0.331% | 0.331% | 0% | 100%
A1020.8 | MD2 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO Comments and Re-submission to KSPL | 0.48% | 2021-08-28 | 2021-09-30 | 1 | 100% | 0.48% | 0.48% | 0% | 100%
A1020.9 | MD2 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.1986% | 2021-09-22 | 2021-10-05 | 1 | 100% | 0.1986% | 0.1986% | 0% | 100%
A1020.10 | MD2 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.149% | 2021-10-06 | 2021-10-15 | 1 | 100% | 0.149% | 0.149% | 0% | 100%
A1020.11 | MD2 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.0662% | 2021-10-16 | 2021-10-20 | 1 | 100% | 0.0662% | 0.0662% | 0% | 100%
A1020.12 | MD2 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.0662% | 2021-10-21 | 2021-10-25 | 1 | 100% | 0.0662% | 0.0662% | 0% | 100%
A1020.13 | MD2 Weighbridge System Package (Rev 1) Review by SO/ NEA(Accepted with comments , Re-submission Required) | 1.159% | 2021-10-29 | 2022-01-21 | 1 | 100% | 1.159% | 1.159% | 0% | 100%
A1020.14 | MD2 Weighbridge System Package (Rev XX) Review by SO/ NEA(Accepted with comments , No Re-submission Required) | 0% | 2022-01-24 | 2023-01-30 | 1 | 100% | 0% | 0% | 0% | 100%
A1020.8 | ED1 AD2 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO Comments and Re-submission to KSPL | 0.48% | 2021-08-28 | 2021-09-30 | 1 | 100% | 0.48% | 0.48% | 0% | 100%
A1020.9 | ED1 AD2 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.1839% | 2021-09-30 | 2021-10-14 | 1 | 100% | 0.1839% | 0.1839% | 0% | 100%
A1020.10 | ED1 AD2 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.1655% | 2021-10-14 | 2021-10-26 | 1 | 100% | 0.1655% | 0.1655% | 0% | 100%
A1020.11 | ED1 AD2 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.01837% | 2021-10-26 | 2021-10-28 | 1 | 100% | 0.01837% | 0.01837% | 0% | 100%
A1020.12 | ED1 AD2 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.01655% | 2021-10-28 | 2021-10-29 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1020.13 | ED1 AD2 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0.1324% | 2021-10-29 | 2021-11-08 | 1 | 100% | 0.1324% | 0.1324% | 0% | 100%
A1020.14 | AD2 Weighbridge System Package (Rev 1) Review by SO/ NEA(Accepted with comments , Re-submission Required) | 1.175% | 2021-10-29 | 2022-01-22 | 1 | 100% | 1.175% | 1.175% | 0% | 100%
A1020.15 | AD2 Weighbridge System Package (Rev XX) Review by SO/ NEA(Accepted with comments , Re-submission Required) | 0% | 2022-01-24 | 2023-07-08 | 1 | 100% | 0% | 0% | 0% | 100%
A1030 | MD3 ED2 ED3 AD3 Preparation, Submission, Review & Acceptance
A1030.1 | MD3 Preparation, Submission, Review & Acceptance
A1030.1 | MD3 Weighbridge System Package (Rev 0a) Preparation by ALC | 0.1655% | 2022-06-25 | 2022-07-06 | 1 | 100% | 0.1655% | 0.1655% | 0% | 100%
A1030.2 | MD3 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.04965% | 2022-07-07 | 2022-07-09 | 1 | 100% | 0.04965% | 0.04965% | 0% | 100%
A1030.3 | MD3 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.1821% | 2022-07-12 | 2022-07-23 | 1 | 100% | 0.1821% | 0.1821% | 0% | 100%
A1030.4 | MD3 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.04965% | 2022-07-25 | 2022-07-27 | 1 | 100% | 0.04965% | 0.04965% | 0% | 100%
A1030.5 | MD3 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.1324% | 2022-07-28 | 2022-08-05 | 1 | 100% | 0.1324% | 0.1324% | 0% | 100%
A1030.6 | MD3 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.08275% | 2022-08-06 | 2022-08-12 | 1 | 100% | 0.08275% | 0.08275% | 0% | 100%
A1030.7 | MD3 Weighbridge System Package (Rev 0) Review by SO/ NEA | 1.092% | 2022-08-13 | 2022-09-01 | 1 | 100% | 1.092% | 1.092% | 0% | 100%
A1030.8 | MD3 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO comments and Re-submission to KSPL | 0.2872% | 2022-09-02 | 2022-09-09 | 1 | 100% | 0.2872% | 0.2872% | 0% | 100%
A1030.9 | MD3 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.01655% | 2022-09-10 | 2022-09-16 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1030.10 | MD3 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.01655% | 2022-09-17 | 2022-09-21 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1030.11 | MD3 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.01655% | 2022-09-22 | 2022-09-29 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1030.12 | MD3 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.01655% | 2022-09-30 | 2022-10-04 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1030.13 | MD3 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0.3393% | 2022-10-05 | 2022-10-25 | 1 | 100% | 0.3393% | 0.3393% | 0% | 100%
A1030.14 | MD3 Weighbridge System Package (Review 2 and above monitored accepted with comments, No Re-submission Required) | 0.4469% | 2022-10-26 | 2022-11-25 | 1 | 100% | 0.4469% | 0.4469% | 0% | 100%
A1030.2 | ED2 Preparation, Submission, Review & Acceptance | 17.68% | 2021-06-18 | 2023-07-14 | 1 | 100% | 17.68% | 17.68% | 0% | 100%
A1030.2.1 | ED2 Weighbridge System Package (Rev 0a) Preparation by ALC | 1.109% | 2021-06-18 | 2021-09-04 | 1 | 100% | 1.109% | 1.109% | 0% | 100%
A1030.2.2 | ED2 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.0331% | 2021-09-06 | 2021-09-07 | 1 | 100% | 0.0331% | 0.0331% | 0% | 100%
A1030.2.3 | ED2 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.1986% | 2021-09-08 | 2021-09-21 | 1 | 100% | 0.1986% | 0.1986% | 0% | 100%
A1030.2.4 | ED2 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.1324% | 2021-09-22 | 2021-09-30 | 1 | 100% | 0.1324% | 0.1324% | 0% | 100%
A1030.2.5 | ED2 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.0993% | 2021-10-01 | 2021-10-07 | 1 | 100% | 0.0993% | 0.0993% | 0% | 100%
A1030.2.6 | ED2 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.1324% | 2021-10-07 | 2021-10-15 | 1 | 100% | 0.1324% | 0.1324% | 0% | 100%
A1030.2.7 | ED2 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0.1821% | 2022-05-06 | 2022-05-18 | 1 | 100% | 0.1821% | 0.1821% | 0% | 100%
A1030.2.8 | ED2 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO comments and Re-submission to KSPL | 0.4965% | 2022-05-19 | 2022-06-22 | 1 | 100% | 0.4965% | 0.4965% | 0% | 100%
A1030.2.9 | ED2 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.0993% | 2022-06-23 | 2022-06-29 | 1 | 100% | 0.0993% | 0.0993% | 0% | 100%
A1030.2.10 | ED2 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.4321% | 2022-06-30 | 2022-08-01 | 1 | 100% | 0.4321% | 0.4321% | 0% | 100%
A1030.2.11 | ED2 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.1177% | 2022-08-02 | 2022-08-11 | 1 | 100% | 0.1177% | 0.1177% | 0% | 100%
A1030.2.12 | ED2 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.1324% | 2022-08-12 | 2022-08-20 | 1 | 100% | 0.1324% | 0.1324% | 0% | 100%
A1030.2.13 | ED2 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0.1655% | 2022-08-23 | 2022-09-02 | 1 | 100% | 0.1655% | 0.1655% | 0% | 100%
A1030.2.14 | ED2 Weighbridge System Package (Review 2 and above monitored accepted with comments, No Re-submission Required) | 0.4487% | 2022-09-05 | 2023-07-14 | 1 | 100% | 0.4487% | 0.4487% | 0% | 100%
A1030.3 | ED3 Preparation, Submission, Review & Acceptance
A1030.3.1 | ED3 Weighbridge System Package (Rev 0a) Preparation by ALC | 0.1821% | 2022-09-03 | 2022-10-05 | 1 | 100% | 0.1821% | 0.1821% | 0% | 100%
A1030.3.2 | ED3 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.0331% | 2022-10-04 | 2022-10-05 | 1 | 100% | 0.0331% | 0.0331% | 0% | 100%
A1030.3.3 | ED3 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.0331% | 2022-10-07 | 2022-10-19 | 1 | 100% | 0.0331% | 0.0331% | 0% | 100%
A1030.3.4 | ED3 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.0331% | 2022-10-20 | 2022-10-26 | 1 | 100% | 0.0331% | 0.0331% | 0% | 100%
A1030.3.5 | ED3 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.0331% | 2022-10-28 | 2022-11-04 | 1 | 100% | 0.0331% | 0.0331% | 0% | 100%
A1030.3.6 | ED3 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.0331% | 2022-11-05 | 2022-11-09 | 1 | 100% | 0.0331% | 0.0331% | 0% | 100%
A1030.3.7 | ED3 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0% | 2022-11-09 | 2022-11-07 | 1 | 100% | 0% | 0% | 0% | 100%
A1030.3.8 | ED3 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO comments and Re-submission to KSPL | 0.09268% | 2022-11-28 | 2022-12-05 | 1 | 100% | 0.09268% | 0.09268% | 0% | 100%
A1030.3.9 | ED3 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.01655% | 2022-12-06 | 2022-12-12 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1030.3.10 | ED3 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0% | 2022-12-13 | 2022-12-16 | 1 | 100% | 0% | 0% | 0% | 100%
A1030.3.11 | ED3 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.01655% | 2022-12-17 | 2022-12-23 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1030.3.12 | ED3 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.0993% | 2022-12-24 | 2022-12-29 | 1 | 100% | 0.0993% | 0.0993% | 0% | 100%
A1030.3.13 | ED3 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0.2979% | 2022-12-31 | 2023-01-19 | 1 | 100% | 0.2979% | 0.2979% | 0% | 100%
A1030.3.13 | ED3 Weighbridge System Package (Review 2 and above monitored accepted with comments, No Re-submission Required) | 0.4469% | 2023-06-21 | 2023-07-22 | 1 | 100% | 0.4469% | 0.4469% | 0% | 100%
A1030.4 | AD3 Preparation, Submission, Review & Acceptance
A1030.4.1 | AD3 Weighbridge System Package (Rev 0a) Preparation by ALC | 2.052% | 2022-02-10 | 2022-07-07 | 1 | 100% | 2.052% | 2.052% | 0% | 100%
A1030.4.2 | AD3 Weighbridge System Package (Rev 0a) Submission to KSPL | 0.2979% | 2022-07-08 | 2022-07-20 | 1 | 100% | 0.2979% | 0.2979% | 0% | 100%
A1030.4.3 | AD3 Weighbridge System Package (Rev 0a) Review (1st Round) | 0.0331% | 2022-07-21 | 2022-07-22 | 1 | 100% | 0.0331% | 0.0331% | 0% | 100%
A1030.4.4 | AD3 Weighbridge System Package (Rev 0a) ALC Ammendment (1st Round) | 0.2979% | 2022-07-22 | 2022-07-28 | 1 | 100% | 0.2979% | 0.2979% | 0% | 100%
A1030.4.5 | AD3 Weighbridge System Package (Rev 0b) Review (2nd Round) | 0.1324% | 2022-07-29 | 2022-09-05 | 1 | 100% | 0.1324% | 0.1324% | 0% | 100%
A1030.4.6 | AD3 Weighbridge System Package (Rev 0b) ALC Ammendment (2nd Round) | 0.0331% | 2022-09-07 | 2022-09-14 | 1 | 100% | 0.0331% | 0.0331% | 0% | 100%
A1030.4.7 | AD3 Weighbridge System Package (Rev 0) Review by SO/ NEA | 0% | 2022-09-14 | 2022-09-27 | 1 | 100% | 0% | 0% | 0% | 100%
A1030.4.8 | AD3 Weighbridge System Package (Rev 1a) Ammendment by ALC on SO comments and Re-submission to KSPL | 0.6124% | 2022-09-29 | 2022-10-04 | 1 | 100% | 0.6124% | 0.6124% | 0% | 100%
A1030.4.9 | AD3 Weighbridge System Package (Rev 1a) Review (1st Round) | 0.331% | 2022-10-05 | 2022-11-30 | 1 | 100% | 0.331% | 0.331% | 0% | 100%
A1030.4.10 | AD3 Weighbridge System Package (Rev 1a) ALC Ammendment (1st Round) | 0.4138% | 2022-12-01 | 2022-12-30 | 1 | 100% | 0.4138% | 0.4138% | 0% | 100%
A1030.4.11 | AD3 Weighbridge System Package (Rev 1b) Review (2nd Round) | 0.1159% | 2022-12-31 | 2023-01-09 | 1 | 100% | 0.1159% | 0.1159% | 0% | 100%
A1030.4.12 | AD3 Weighbridge System Package (Rev 1b) ALC Ammendment (2nd Round) | 0.0662% | 2023-01-10 | 2023-01-13 | 1 | 100% | 0.0662% | 0.0662% | 0% | 100%
A1030.4.13 | AD3 Weighbridge System Package (Rev 1) Review by SO/ NEA | 0% | 2023-01-14 | 2023-02-04 | 1 | 100% | 0% | 0% | 0% | 100%
A1030.4.14 | AD3 Weighbridge System Package (Review 2 and above monitored accepted with comments, No Re-submission Required) | 0.2648% | 2023-06-21 | 2023-07-10 | 1 | 100% | 0.2648% | 0.2648% | 0% | 100%
A1085 | Traffic Modelling
A1085.T.01 | Award Traffic Modelling Consultant | 0.01655% | 2022-02-07 | 2022-02-07 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1085.T.02 | Kick-off Meeting | 0.02582% | 2022-02-22 | 2022-02-23 | 1 | 100% | 0.02582% | 0.02582% | 0% | 100%
A1085.T.03 | First round of model findings in slides [Rev 0a] | 0.4634% | 2022-02-24 | 2022-03-28 | 1 | 100% | 0.4634% | 0.4634% | 0% | 100%
A1085.T.04 | Comments on Rev 0a findings (allowing time for possible discussion and presentation) | 0.1159% | 2022-03-29 | 2022-04-05 | 1 | 100% | 0.1159% | 0.1159% | 0% | 100%
A1085.T.05 | Second round of model findings in slides [Rev 0b] | 0.0331% | 2022-04-06 | 2022-04-07 | 1 | 100% | 0.0331% | 0.0331% | 0% | 100%
A1085.T.06 | Submit to SO/ NEA [Rev 0] | 1.026% | 2022-04-08 | 2022-06-22 | 1 | 100% | 1.026% | 1.026% | 0% | 100%
A1085.T.07 | Third round of model findings in slides [Rev 1a] | 2.203% | 2022-06-23 | 2022-11-29 | 1 | 100% | 2.203% | 2.203% | 0% | 100%
A1085.T.08 | Comments on Rev 1a findings (allowing time for possible discussion and presentation) | 0.04965% | 2022-09-30 | 2022-10-03 | 1 | 100% | 0.04965% | 0.04965% | 0% | 100%
A1085.T.09 | Fourth round of model findings in slides [Rev 1b] | 0.1177% | 2022-10-04 | 2022-10-12 | 1 | 100% | 0.1177% | 0.1177% | 0% | 100%
A1085.T.10 | Submit to SO/ NEA [Rev 1] | 0.5645% | 2022-10-13 | 2022-12-05 | 1 | 100% | 0.5645% | 0.5645% | 0% | 100%
A1085.T.11 | Fifth round of model findings in slides [Rev 2a] | 0.01655% | 2022-12-06 | 2022-12-13 | 1 | 100% | 0.01655% | 0.01655% | 0% | 100%
A1085.T.12 | Comments on Rev 2a findings (allowing time for possible discussion and presentation) | 0% | 2022-12-14 | 2022-12-23 | 1 | 100% | 0% | 0% | 0% | 100%
A1085.T.13 | Sixth round of model findings in slides [Rev 2b] | 0% | 2022-12-24 | 2023-01-03 | 1 | 100% | 0% | 0% | 0% | 100%
A1085.T.14 | Submit to SO/ NEA [Rev 2] | 0% | 2023-01-04 | 2023-01-14 | 1 | 100% | 0% | 0% | 0% | 100%
A1085.T.15 | Final Model findings report | 0.1821% | 2023-01-16 | 2023-01-21 | 1 | 100% | 0.1821% | 0.1821% | 0% | 100%
A1085.T.16 | Final presentation / confirmation on findings | 2.466% | 2023-01-25 | 2023-02-03 | 1 | 100% | 2.466% | 2.466% | 0% | 100%
A1085.T.17 | Comments on final report | 0.811% | 2023-02-06 | 2023-02-08 | 1 | 100% | 0.811% | 0.811% | 0% | 100%
A1085.T.18 | Submit & Confirmation of final report by SO/NEA | 0.0662% | 2023-02-09 | 2023-02-13 | 1 | 100% | 0.0662% | 0.0662% | 0% | 100%
A1050 | Procurement
A1050.P.01 | Weighbridges | 1.787% | 2022-08-26 | 2023-03-15 | 1 | 100% | 1.787% | 1.787% | 0% | 100%
A1050.P.02 | Furniture | 0.8606% | 2023-02-14 | 2023-04-15 | 1 | 95% | 0.8176% | 0.8606% | -0.04303% | 95%
A1050.P.03 | UPS & 19" Racks | 0% | 2022-10-18 | 2023-03-16 | 1 | 100% | 0% | 0% | 0% | 100%
A1050.P.04 | Public Announcement System | 0.4469% | 2021-07-05 | 2023-03-16 | 1 | 85% | 0.3798% | 0.4469% | -0.06703% | 85%
A1050.P.05 | Electrical & Structured Cabling Services(By Others) | 0.4469% | 2023-02-14 | 2023-03-16 | 1 | 0% | 0% | 0.4469% | -0.4469% | 0%
A1050.P.06 | Data Processing Equipment | 0.4469% | 2022-05-25 | 2023-03-16 | 1 | 100% | 0.4469% | 0.4469% | 0% | 100%
A1050.P.07 | Data Communication Equipment | 0.4469% | 2022-05-25 | 2023-03-16 | 1 | 95% | 0.4245% | 0.4469% | -0.02234% | 95%
A1050.P.08 | Station Integrated with Interfacing Controller for Receipt, Intercom, RFID, Biometrics, Traffic Lights, Vehicle Barrier | 0.4469% | 2022-05-25 | 2023-03-16 | 1 | 95% | 0.4245% | 0.4469% | -0.02234% | 95%
A1050.P.09 | Video Recording System, LPR Hardware and Accessories | 0.5958% | 2022-05-25 | 2023-03-27 | 1 | 95% | 0.566% | 0.5958% | -0.02979% | 95%
A1050.P.10 | Zonal Detection System | 0.8441% | 2022-05-25 | 2023-04-14 | 1 | 90% | 0.7597% | 0.8441% | -0.08441% | 90%
A1050.P.11 | Radioactive Devices | 0.8606% | 2022-08-29 | 2023-04-15 | 1 | 100% | 0.8606% | 0.8606% | 0% | 100%
A1050.P.12 | Heat Detection Devices | 1.49% | 2022-08-09 | 2023-03-10 | 1 | 100% | 1.49% | 1.49% | 0% | 100%
A1050.P.13 | Ash Truck Positioning and Empty/Full Detection Devices | 0.8606% | 2022-05-25 | 2023-04-15 | 1 | 90% | 0.7746% | 0.8606% | -0.08606% | 90%
A1050.P.14 | Purchase and Delivery of Casted Items(Others) -Batch 1 | 1.159% | 2023-06-09 | 2023-06-10 | 1 | 100% | 1.159% | 1.159% | 0% | 100%
A1050.P.15 | Purchase and Delivery of Casted Items(Others) - Batch 2 | 1.274% | 2023-06-10 | 2023-06-10 | 1 | 100% | 1.274% | 1.274% | 0% | 100%
0 | Manufacture / Fabrication / Delivery
A1060 | Manufacture Commence Data (Commence Date should be notified by KSPL)
A1060.M.01 | Weighbridges | 0.8937% | 2023-03-16 | 2023-05-20 | 1 | 100% | 0.8937% | 0.8937% | 0% | 100%
A1060.M.02 | Furniture | 0.4469% | 2023-04-17 | 2023-05-19 | 1 | 0% | 0% | 0.4469% | -0.4469% | 0%
A1060.M.03 | UPS & 19" Racks | 0.8937% | 2023-03-17 | 2023-05-22 | 1 | 80% | 0.715% | 0.8937% | -0.1787% | 80%
A1060.M.04 | Public Announcement System | 0.5793% | 2023-03-17 | 2023-04-28 | 1 | 50% | 0.2896% | 0.5793% | -0.2896% | 50%
A1060.M.05 | Electrical & Structured Cabling Services | 1.324% | 2023-03-17 | 2023-06-21 | 1 | 0% | 0% | 1.324% | -1.324% | 0%
A1060.M.06 | Data Processing Equipment | 0.8937% | 2023-03-17 | 2023-05-22 | 1 | 50% | 0.4469% | 0.8937% | -0.4469% | 50%
A1060.M.07 | Data Communication Equipment | 0.8937% | 2023-05-02 | 2023-07-04 | 1 | 50% | 0.4469% | 0.8937% | -0.4469% | 50%
A1060.M.08 | Station Integrated with Interfacing Controller for Receipt, Intercom, RFID, Biometrics, Traffic Lights, Vehicle Barrier | 1.324% | 2023-03-17 | 2023-06-21 | 1 | 65% | 0.8606% | 1.324% | -0.4634% | 65%
A1060.M.09 | Video Recording System, LPR Hardware and Accessories | 1.043% | 2023-03-28 | 2023-06-12 | 1 | 75% | 0.782% | 1.043% | -0.2607% | 75%
A1060.M.10 | Zonal Detection System | 1.324% | 2023-05-23 | 2023-08-25 | 1 | 35% | 0.4634% | 1.324% | -0.8606% | 35%
A1060.M.11 | Radioactive Devices | 0.5958% | 2023-04-17 | 2023-05-30 | 1 | 90% | 0.5362% | 0.5958% | -0.05958% | 90%
A1060.M.12 | Heat Detection Devices | 0.7448% | 2023-03-11 | 2023-05-05 | 1 | 90% | 0.6703% | 0.7448% | -0.07448% | 90%
A1060.M.13 | Ash Truck Positioning and Empty/Full Detection Devices | 0.8937% | 2023-04-17 | 2023-06-20 | 1 | 40% | 0.3575% | 0.8937% | -0.5362% | 40%
A1070 | Completion of FAT for Weighbridge System
A1070.F.01 | FAT for Weighbridge | 0.8441% | 2023-07-24 | 2023-09-21 | 1 | 0% | 0% | 0.8441% | -0.8441% | 0%
A1070.F.02 | FAT for Zonal Detection | 0.7448% | 2023-08-26 | 2023-10-17 | 1 | 0% | 0% | 0.7448% | -0.7448% | 0%
A1070.F.03 | FAT for Ash Truck Positioning and Empty/Full Detection Devices | 0.7448% | 2023-07-05 | 2023-08-26 | 1 | 0% | 0% | 0.7448% | -0.7448% | 0%
A1070.F.04 | Preparation of Holding Area for weighbridge platforms | 0.0662% | 2023-10-20 | 2023-10-24 | 1 | 0% | 0% | 0.0662% | -0.0662% | 0%
A1080 | Delivery to Site
A1080.D.00 | Architectural and Building Service Works | 0.01473% | 2023-09-22 | 2023-09-22 | 1 | 0% | 0% | 0.01473% | -0.01473% | 0%
A1080.D.01 | Weighbridge System delivery | 5.71% | 2023-10-25 | 2024-01-02 | 1 | 0% | 0% | 5.71% | -5.71% | 0%
A1080.D.02 | Other Weighbridge Equipments | 0.9434% | 2023-10-25 | 2024-01-02 | 1 | 0% | 0% | 0.9434% | -0.9434% | 0%
A1080.D.03 | Weighbridge Platform | 0% | 2023-10-25 | 2024-01-02 | 1 | 100% | 0% | 0% | 0% | 100%
A1080.D.04 | Zonal Detection System delivery | 0.5958% | 2023-10-25 | 2023-12-06 | 1 | 0% | 0% | 0.5958% | -0.5958% | 0%
A1080.D.05 | Ash Truck Positioning and Empty/Full Detection Devices delivery | 0.5958% | 2023-10-25 | 2023-12-06 | 1 | 0% | 0% | 0.5958% | -0.5958% | 0%
A1090 | Installation
A1090.I.01 | Weighbridge Foundation & Control Room ready for Installation | 0.04965% | 2024-01-03 | 2024-01-05 | 1 | 0% | 0% | 0.04965% | -0.04965% | 0%
A1090.I.02 | Electrical and instrumentation works | 0.01655% | 2024-01-06 | 2024-01-06 | 1 | 0% | 0% | 0.01655% | -0.01655% | 0%
A1090.I.03 | Public Announcement System | 0.5958% | 2024-01-08 | 2024-02-20 | 1 | 0% | 0% | 0.5958% | -0.5958% | 0%
A1090.I.04 | Weighbridges | 1.589% | 2024-01-19 | 2024-05-15 | 1 | 0% | 0% | 1.589% | -1.589% | 0%
A1090.I.05 | Furniture | 0.2979% | 2024-01-08 | 2024-01-27 | 1 | 0% | 0% | 0.2979% | -0.2979% | 0%
A1090.I.06 | Rack | 0.2979% | 2024-01-08 | 2024-01-27 | 1 | 0% | 0% | 0.2979% | -0.2979% | 0%
A1090.I.07 | UPS | 0.2979% | 2024-01-08 | 2024-01-27 | 1 | 0% | 0% | 0.2979% | -0.2979% | 0%
A1090.I.08 | Data Processing System (DPS) | 0.4469% | 2024-01-08 | 2024-02-07 | 1 | 0% | 0% | 0.4469% | -0.4469% | 0%
A1090.I.09 | Data Communication System | 0.4469% | 2024-01-08 | 2024-02-07 | 1 | 0% | 0% | 0.4469% | -0.4469% | 0%
A1090.I.10 | Interfacing Controller (IFC) | 0.2979% | 2024-01-08 | 2024-01-27 | 1 | 0% | 0% | 0.2979% | -0.2979% | 0%
A1090.I.11 | Weighbridge Intercom Kiosk | 0.8275% | 2024-01-08 | 2024-03-07 | 1 | 0% | 0% | 0.8275% | -0.8275% | 0%
A1090.I.12 | EPS Antenna | 0.4303% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4303% | -0.4303% | 0%
A1090.I.13 | Traffic Lights | 0.4303% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4303% | -0.4303% | 0%
A1090.I.14 | Barriers | 0.4303% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4303% | -0.4303% | 0%
A1090.I.15 | License Plate Recognition System (LPR) | 0.4303% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4303% | -0.4303% | 0%
A1090.I.16 | Video Recording System (VRS) | 0.4303% | 2024-01-08 | 2024-02-06 | 1 | 0% | 0% | 0.4303% | -0.4303% | 0%
A1090.I.17 | Radioactive Devices | 0.3972% | 2024-01-08 | 2024-02-03 | 1 | 0% | 0% | 0.3972% | -0.3972% | 0%
A1090.I.18 | Load Heat Detection Devices | 0.3972% | 2024-01-08 | 2024-02-03 | 1 | 0% | 0% | 0.3972% | -0.3972% | 0%
A1090.I.19 | Single weighbridge physical mock-up | 0.6124% | 2024-01-08 | 2024-02-21 | 1 | 0% | 0% | 0.6124% | -0.6124% | 0%
A1090.I.20 | Zonal Detection System | 0.6289% | 2024-01-08 | 2024-02-22 | 1 | 0% | 0% | 0.6289% | -0.6289% | 0%
A1090.I.21 | Ash Truck Positioning and Empty/Full Detection Devices | 0.8275% | 2024-01-08 | 2024-03-07 | 1 | 0% | 0% | 0.8275% | -0.8275% | 0%
0 | Testing & Commissioning
A1100 | ERP/ DCS Interface Readiness | 0.01655% | 2024-05-30 | 2024-05-30 | 1 | 0% | 0% | 0.01655% | -0.01655% | 0%
A1110 | Site Acceptance Test
A1110.S.01 | Client Inspection of Weighbridge Sub-system | 0.4138% | 2024-05-31 | 2024-06-29 | 1 | 0% | 0% | 0.4138% | -0.4138% | 0%
A1110.S.02 | Client Inspection of Zonal Detection Sub-system | 0.4469% | 2024-07-01 | 2024-07-31 | 1 | 0% | 0% | 0.4469% | -0.4469% | 0%
A1110.S.03 | Punchlist Clearance | 0.331% | 2024-08-01 | 2024-08-23 | 1 | 0% | 0% | 0.331% | -0.331% | 0%
A1110.S.04 | User Training | 0.2979% | 2024-08-24 | 2024-09-13 | 1 | 0% | 0% | 0.2979% | -0.2979% | 0%
A1120 | System Commissioning Test
A1120.S.01 | Weighbridge (Line 1&2) System Conduct System Commissioning Test - Hardware | 1.324% | 2024-09-14 | 2024-12-16 | 1 | 0% | 0% | 1.324% | -1.324% | 0%
A1120.S.02 | Weighbridge (Line 1&2) System Conduct System Commissioning Test - Software | 1.324% | 2024-09-14 | 2024-12-16 | 1 | 0% | 0% | 1.324% | -1.324% | 0%
A1120.S.03 | Weighbridge Zonal System Conduct System Commissioning Test | 1.324% | 2024-09-14 | 2024-12-16 | 1 | 0% | 0% | 1.324% | -1.324% | 0%
A1120.S.04 | Weighbridge (Line 3&4) System Commissioning Test | 1.324% | 2024-12-17 | 2025-03-19 | 1 | 0% | 0% | 1.051% | -1.051% | 0%
A1130 | Successful Completion of Trial Operation Test | 1.572% | 2025-03-21 | 2025-07-09 | 1 | 0% | 0% | 0% | 0% | 0%
A1150 | Completion of the whole Sub-Contract Works | 0.8937% | 2025-07-10 | 2025-10-07 | 1 | 0% | 0% | 0% | 0% | 0%
Formulas:
Start = [2]ALC!D8
Finish = [2]ALC!E8